## Sheet1
Global HRAC Action Register
Action | Owner | Initiated | Status | Due | Comments
Contact CLI about facilitating strategy session | Arlene | 2016-02-07 | Complete |  | Robert Hunter of CLI to prepare documents
Determine timing for strategy session | Mark/Michael | 2016-02-07 | Complete |  | Proposal for week of Sept 12
Develop HRAC BMPs | Tim | 2016-02-07
Symposium proposal for 2017 GHRC | AWG | 2016-02-07 | In-progress |  | Proposal communicated to Todd Gaines and is under consideration.
Develop HRAC recommendations for resistance testing | Working groups | 2016-02-07 | Ongoing | Q42016
ETS response | Bob/Michael/Mark | 2016-02-07 | Complete |  | Communicated to Keith Jones