## Sheet1
Global HRAC Action Register
Action | Owner | Initiated | Status | Due | Comments
Contact CLI about facilitating strategy session | Arlene | 2016-02-07 | Complete |  | Robert Hunter of CLI to prepare documents
Determine timing for strategy session | Mark/Michael | 2016-02-07 | Complete |  | Proposal for week of Sept 12
Develop HRAC BMPs | Tim | 2016-02-07 | Complete
Symposium proposal for 2017 GHRC | AWG | 2016-02-07 | Complete |  | Proposal accepted by Planning Committee
Develop HRAC recommendations for resistance testing | Working groups | 2016-02-07 | Ongoing | Q4-2016
ETS response | Bob/Michael/Mark | 2016-02-07 | Complete |  | Communicated to Keith Jones
Website Launch | Arlene |  | Complete | 2016-07-01
Finalize Strategy Session | Mark |  | Complete | 2016-07-01
New contract for Ian Heap | Arlene and Dawn |  | Complete | Q4-2016
Discuss Intl Survey Succession w/Ian | Arlene | 2016-09-22 | Complete | Q1-2017 | Agreed and CLI legal will draft language for next agreement
Intl Survey site enhancements | Arlene | 2016-09-22 | Started
Set up Issues Management Working Group | Mark and Harry | 2016-09-22 | Started | Q4-2016 | Draft charter created
Prioritze technical items/issues for update | Mark and Harry | 2016-09-22 |  | Q4-2016
Set up structure to share new research | Roland | 2016-09-22 |  | Q1-2017
Integrate all RACs across CLI | Robert H. | 2016-09-22
Connect GHRAC with regionals | Michael, Robert, Rolando | 2016-09-22 |  | Q1-2017
Plans for next face to face mtg | Exec Committee | 2016-09-22 | In Progress | Q1-2017 | In conjunction with GHRC 2017
Update AWG Fact Sheets | Bob Masters | 2016-09-22 |  | Q1-2017 | Create schedule for updates